## Sheet1
Sprints
| 1 | 22-Aug-2016 to 02-Sep-2016 | 10d
| 2 | 05-Sep-2016 to 16-Sep-2016 | 10d
| 3 | 19-Sep-2016 to 30-Sep-2016 | 9d
| 4 | 3-Oct-2016 to 21-Oct-2016 | 10d(1 week holiday in between)
S.No | Outputs | Sub-Tasks | Assignee | Sprint
1 | Basic Layout | Base Layout Design | Sraddha | Sprint 1
|  | Place holders and Buttons | Sraddha
|  | Develop skin(css) | Sraddha
|  | Show/hide API window | Sraddha
|  | Change request (if any) | Sraddha
2 | Add Customer | Add customer template | Sraddha | Sprint 1
|  | Input validation | Sraddha
|  | Load data from init file and bind data | Sraddha / Krishnendu
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Service layer Api calls (backend calls) | Krishnendu
|  | Response JSON parser | Krishnendu
|  | Mouse hover info (UI) | Sraddha
3 | Add Cloud Sites | Add cloud site template | Sraddha | Sprint 2
|  | Input validation | Sraddha
|  | Load data from init file and bind data | Sraddha / Krishnendu
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Service layer Api calls (backend calls) | Krishnendu
|  | Response JSON parser | Krishnendu
|  | Mouse hover info (UI) | Sraddha
|  | Drawing Library Wrapper | Krishnendu
|  | Node position calculator | Krishnendu
|  | Node connection Map (local storage data) | Krishnendu
|  | Polling for node state (backend calls) | Krishnendu
4 | Add External Sites | Add external site template | Sraddha | Sprint 2
|  | Input validation (Form validation) | Sraddha
|  | Input validation (App validation) | Sraddha
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Mouse hover info (UI) | Sraddha
|  | Node draw module | Krishnendu
|  | Drawing Library Wrapper | Krishnendu
|  | Node position calculator | Krishnendu
|  | Node connection Map (local storage data) | Krishnendu
5 | Connect Sites | Connect sites template | Sraddha | Sprint 2
|  | Input validation (Form validation) | Sraddha
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Mouse hover info (UI) | Sraddha
|  | Drawing Library Wrapper | Krishnendu
|  | Node position calculator | Krishnendu
|  | Node connection Map (local storage data) | Krishnendu
6 | Add VMs | Add VM template | Sraddha | Sprint 3
|  | Input validation (Form validation) | Sraddha
|  | Load data from init file and bind data | Sraddha / Krishnendu
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Mouse hover info (UI) | Sraddha
|  | Drawing Library Wrapper | Krishnendu
|  | Node position calculator | Krishnendu
|  | Node connection Map (local storage data) | Krishnendu
|  | Polling for node state (backend calls) | Krishnendu
7 | Right Click | Start, Stop, Reboot | Krishnendu | Sprint 3
|  | Delete Vm | Krishnendu
|  | VM console | Krishnendu
|  | Local storage design | Krishnendu
|  | Add / remove api for local storage | Krishnendu
|  | Mouse hover info (UI) | Sraddha
|  | Drawing Library Wrapper | Krishnendu
|  | Node position calculator | Krishnendu
|  | Node connection Map (local storage data) | Krishnendu
8 | Reset | Reset Vm | Sraddha | Sprint 3
|  | Reset All | Sraddha
9 | Acceptance Testing and Fine-tuning | Testing Bug-Fixing Fine-tuning | Sraddha/Krishnendu | Sprint 4